PROJECT MANAGEMENT PLAN

DXM PULSE

Digital Experience Management Platform

| Document ID | DXM-PMP-2026-001 |
| --- | --- |
| Version | 1.0 |
| Date | March 23, 2026 |
| Status | Active |
| Classification | Internal / Confidential |
| Project Manager | DXM Product Lead |
| Methodology | Agile (Sprint-Based) |
| Current Phase | Sprint 12 Complete — Sprint 13 Starting |

# Table of Contents

# 1. Project Overview

## 1.1 Project Summary

Project Name: DXM Pulse — Digital Experience Management Platform

Project Type: SaaS Product Development (MVP → Production)

Domain: Web Analytics, Session Replay, and Client Reporting for Digital Agencies

Target Market: Ethiopian digital agencies managing 2–50 client websites

Business Model: Freemium SaaS (Free / Starter 499 ETB / Pro 1,499 ETB monthly)

Start Date: February 2026

Current Status: Feature-complete MVP, entering Production Readiness + Observability phase

## 1.2 Project Objectives

- Deliver a self-hosted analytics platform that agencies can use to track, analyze, and report on client websites

- Provide session replay capability competing with Hotjar/FullStory at a fraction of the cost

- Enable automated alerting for performance and UX issues across a portfolio of sites

- Support local payment processing via Chapa (Ethiopian payment gateway)

- Achieve production-ready stability with monitoring, error tracking, and structured logging

## 1.3 Success Criteria

| # | Criterion | Metric | Status |
| --- | --- | --- | --- |
| 1 | Core features functional (dashboard, replay, alerts, billing, reports) | All features accessible and working | Complete |
| 2 | SDK tracks events reliably across client websites | <2KB gzipped, sendBeacon transport, offline resilience | Complete |
| 3 | Payment flow completes end-to-end with Chapa | Initiate → pay → webhook → plan activation | Complete |
| 4 | System handles real-world traffic without crashes | Error boundary, rate limiting, structured logging | Complete |
| 5 | Production monitoring in place before user onboarding | Sentry, request IDs, health checks, uptime monitor | In Progress |
| 6 | First 5 agency users onboarded successfully | Signup → install SDK → first insight generated | Planned |
| 7 | System performs acceptably on slower networks | Bundle <250KB initial, lazy-loaded pages | Planned |

## 1.4 Key Stakeholders

| Stakeholder | Role | Responsibility |
| --- | --- | --- |
| Product Lead | Project Manager + Product Owner | Sprint planning, prioritization, user research, go/no-go decisions |
| Development (Claude AI) | Full-Stack Engineer | Architecture, implementation, code review, documentation generation |
| Target Agencies | End Users / Beta Testers | Feedback on UX, feature requests, real-world validation |
| Operations | DevOps / Infrastructure | Server provisioning, deployment, backup, monitoring setup |

# 2. Development Methodology

## 2.1 Approach

DXM Pulse uses a sprint-based agile methodology with the following characteristics:

- Sprint Duration: 1–3 days per sprint (rapid iteration, single-developer velocity)

- Sprint Cycle: Plan → Review → Approve → Implement → Verify → Next

- No Standups: Single developer + AI pair programming eliminates ceremony overhead

- Continuous Integration: Build verification after every sprint (tsc + vite build)

- Documentation: SDLC documents generated in parallel with implementation (not deferred)

## 2.2 Sprint Philosophy

The project follows a deliberately ordered sprint philosophy optimized for real-world impact:

- Observability before Testing — Monitor production first, then write tests based on what actually breaks

- Deploy early — Get real users before perfecting every edge case

- Product decisions > Engineering decisions — Don’t overbuild, get feedback early

- No new features after MVP complete — Stability and reliability take priority

- Minimal changes — Every sprint solves a specific problem with the smallest possible change

## 2.3 Definition of Done

A sprint is considered complete when:

- All planned features are implemented and functional

- Both apps build cleanly (tsc for API, vite for Web) with no new errors

- No regressions in existing functionality (manual verification)

- Code follows existing patterns and conventions

- No new dependencies introduced without explicit justification

- Sprint deliverables reviewed and approved by Product Lead

## 2.4 Change Control

Changes to sprint scope follow a lightweight process:

- Minor adjustments (within sprint): Handled inline during implementation

- Scope additions: Deferred to next sprint unless critical for current sprint’s goal

- Architecture changes: Require explicit plan → review → approve cycle before implementation

- Dependency additions: Must be justified and approved (strong bias against new dependencies)

# 3. Work Breakdown Structure (Sprint History)

## 3.1 Phase 1: Foundation (Sprints 1–4)

| Sprint | Name | Deliverables | Status |
| --- | --- | --- | --- |
| 1 | Project Setup + Auth | Monorepo structure (apps/api, apps/web, packages/) Express API with SQLite + WAL JWT auth (signup, login, logout, refresh) React SPA with AuthContext + ProtectedRoute Zod validation on all endpoints | Complete |
| 2 | SDK + Data Collection | dxm.js tracking SDK (<2KB gzipped) Event queue with localStorage persistence POST /collect endpoint with session upsert Core Web Vitals capture (LCP, CLS, FCP, INP, TTFB) Session replay recording via rrweb | Complete |
| 3 | Dashboard + Analytics | Portfolio overview page with site cards Site detail page with session list Click heatmaps visualization Performance metrics (vitals charts) Session replay player | Complete |
| 4 | Onboarding + Site Management | Multi-step onboarding wizard Site CRUD (create, edit, delete) SDK installation guide with copy-to-clipboard Site verification (await first session) Workspace profile collection | Complete |

## 3.2 Phase 2: Intelligence (Sprints 5–8)

| Sprint | Name | Deliverables | Status |
| --- | --- | --- | --- |
| 5 | Insights Engine | 5 automated detectors (bounce, duration, activity, traffic drop/growth) Severity tiers (info, warning, critical) 6-hour cooldown + deduplication Auto-resolve when conditions clear Insights list page with severity badges | Complete |
| 6 | AI Brief System | Deterministic brief generation (no LLM) 4 brief types: overview, site, alert, funnel Cache-aside pattern with TTL (ai_artifacts table) Stable hash for cache invalidation Brief display in overview + site detail pages | Complete |
| 7 | Funnel Analysis | Funnel CRUD (name, steps with URL patterns) Funnel analysis engine (step-by-step conversion) Drop-off visualization AI funnel briefs Feature-gated (Starter+) | Complete |
| 8 | Settings + Notifications | Workspace settings page Telegram bot integration (alerts + digest) Email notification preferences Weekly digest engine (systemd timer) Team member management (invite, roles) | Complete |

## 3.3 Phase 3: Monetization (Sprints 9–10.5)

| Sprint | Name | Deliverables | Status |
| --- | --- | --- | --- |
| 9 | Alerts Management Page | Alert list with filters (site, severity, status) Alert detail view with affected sessions Resolve/unresolve actions Alert engine: rage clicks, slow loads, high bounce Telegram + email notifications | Complete |
| 10 | Billing Flow (Chapa E2E) | Plan catalog display (Free/Starter/Pro) Chapa payment initiation HMAC webhook verification (timing-safe) Idempotent plan activation Upgrade request tracking Feature gating (API + frontend UpgradeGate) | Complete |
| 10.5 | Billing Polish Pass | Confirmation screen (plan/amount/reference cards) Transaction reference display + localStorage persistence Timeout UX (refresh + support link) Payment locking (prevent double-submit) Analytics tracking (console.info billing events) Telegram manual-activation polling URL param clearing after redirect | Complete |

## 3.4 Phase 4: Reporting (Sprints 11–11.6)

| Sprint | Name | Deliverables | Status |
| --- | --- | --- | --- |
| 11 | Reports + Client Export | Reports page with site selector Report builder (pure frontend transformation) ReportView component (executive summary, KPIs, insights, top pages) PDF export (window.print) CSV export (downloadCsv utility) | Complete |
| 11.5 | Reports Enhancement | Period comparison (7d vs previous 7d) TrendBadge with semantic coloring (invertedTrend) Bounce proxy per page (% sessions < 10s) Data-specific recommendations Trend-aware executive summary | Complete |
| 11.6 | Decision Layer UI | Key Takeaways block (positives/negatives/primaryFocus) Primary Action card (single most important action) GOOD/BAD labels on trend indicators Confidence indicator (High/Medium/Low based on session count) Recommendation priority upgrade | Complete |

## 3.5 Phase 5: Production Readiness (Sprint 12)

| Sprint | Name | Deliverables | Status |
| --- | --- | --- | --- |
| 12 | Production Readiness | ErrorBoundary (React class component + Sentry hook) NotFoundPage (404 for unknown routes) Security headers middleware (CSP, HSTS, nosniff) Enhanced health check (/health with DB ping, uptime) SMTP email wiring (conditional: real SMTP or console) Structured logger (JSON, levels, timestamps) SEO meta polish (Twitter cards, robots) .env.example for deployment reference | Complete |

## 3.6 Phase 6: Launch Preparation (Sprints 13–17)

| Sprint | Name | Deliverables | Status |
| --- | --- | --- | --- |
| 13 | Observability + Monitoring | Sentry SDK (frontend + backend, exceptions only) Request correlation IDs (X-Request-Id everywhere) Structured request logging (replace morgan) Uptime monitoring endpoint Source map consideration for stack traces | In Progress |
| 14 | Performance + Code Splitting | Lazy-load all page components Bundle size optimization (split 547KB chunk) Image lazy loading + SVG optimization API response caching headers Session replay load optimization | Planned |
| 15 | Testing + CI Pipeline | Fix better-sqlite3 Node.js version mismatch Integration tests for critical paths (auth, billing, collect) GitHub Actions CI: lint → build → test Pre-commit type checking hook | Planned |
| 16 | Multi-User + Permissions | Team invite flow (email invitation) Role-based access enforcement (owner/admin/viewer) Audit log for sensitive actions Per-user notification preferences | Planned |
| 17 | Landing Page + Growth | Landing page redesign with product screenshots Interactive demo mode (pre-loaded sample data) Onboarding checklist (SDK → session → insight → team) Email drip sequence (day 1/3/7) | Planned |

# 4. Project Timeline

## 4.1 Milestone Schedule

| # | Milestone | Target Date | Dependencies | Status |
| --- | --- | --- | --- | --- |
| M1 | Feature-Complete MVP | March 20, 2026 | Sprints 1–11.6 | Complete |
| M2 | Production-Ready Build | March 23, 2026 | Sprint 12 | Complete |
| M3 | Observability Live | March 26, 2026 | Sprint 13 + Sentry setup | In Progress |
| M4 | Performance Optimized | March 30, 2026 | Sprint 14 | Planned |
| M5 | CI/CD Pipeline Green | April 5, 2026 | Sprint 15 + Node.js fix | Planned |
| M6 | Beta Launch (5 agencies) | April 8, 2026 | M3 + M4 minimum | Planned |
| M7 | Multi-User Ready | April 15, 2026 | Sprint 16 | Planned |
| M8 | Public Launch | April 25, 2026 | Sprint 17 + landing page | Planned |

## 4.2 Critical Path

The critical path to Beta Launch (M6) requires only Sprints 13 + 14:

- Sprint 13 (Observability) — Without monitoring, production issues are invisible. BLOCKER for any real user traffic.

- Sprint 14 (Performance) — 547KB bundle on Ethiopian networks is noticeable. Required for acceptable UX.

- After M3 + M4: System is deployable and monitorable. Beta users can be onboarded.

- Sprint 15 (Testing) can run in parallel with beta onboarding — tests informed by real usage.

- Sprint 16–17 are growth features, not launch blockers.

## 4.3 Gantt Chart (Text)

Timeline in weekly blocks (W = week starting date):

| Activity | W Mar 17 | W Mar 24 | W Mar 31 | W Apr 7 | W Apr 14 | W Apr 21 |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 12: Prod Ready | ███ |  |  |  |  |  |
| Sprint 13: Observability |  | ▒▒▒ |  |  |  |  |
| Sprint 14: Performance |  |  | ░░░ |  |  |  |
| M6: Beta Launch |  |  |  | ◆ MILE |  |  |
| Sprint 15: Testing + CI |  |  |  | ░░░ |  |  |
| Sprint 16: Multi-User |  |  |  |  | ░░░ |  |
| Sprint 17: Landing + Growth |  |  |  |  |  | ░░░ |
| M8: Public Launch |  |  |  |  |  | ◆ MILE |

Legend: ███ Complete   ▒▒▒ In Progress   ░░░ Planned   ◆ Milestone

# 5. Resource Plan

## 5.1 Team Composition

| Role | Resource | Allocation | Duration |
| --- | --- | --- | --- |
| Product Lead / PM | Human (Project Owner) | Part-time (sprint planning, review, decisions) | Ongoing |
| Full-Stack Developer | Claude AI (Pair Programming) | On-demand per sprint | Ongoing |
| DevOps / Operations | Human (setup) + Automation | Burst (deployment setup), then monitoring | Sprint 12–13 |
| Beta Testers | 5 target agencies | Feedback sessions, bug reports | Sprint 14+ |

## 5.2 Technology Stack

| Layer | Technology | Justification |
| --- | --- | --- |
| Backend | Node.js + Express + TypeScript | Fast iteration, single-language stack, strong typing |
| Database | SQLite + better-sqlite3 | Zero-ops, WAL for concurrency, sufficient for MVP scale |
| Frontend | React 18 + Vite + TailwindCSS | Fast dev builds, modern UI, lazy loading support |
| SDK | Vanilla JS + rrweb | Minimal footprint (<2KB), no framework dependency |
| Auth | JWT + bcrypt + httpOnly cookies | Stateless, secure, standard approach |
| Payments | Chapa (Ethiopian gateway) | Local ETB currency support, webhook-based activation |
| Email | Nodemailer (conditional SMTP) | Zero-cost dev mode, real delivery in production |
| Validation | Zod | TypeScript-first, runtime validation with type inference |
| Monitoring | Sentry (planned) | Industry standard, free tier sufficient for MVP |
| Deployment | Linux VPS + Caddy + systemd | Simple, cost-effective, auto-TLS |

## 5.3 Infrastructure

| Component | Specification | Cost |
| --- | --- | --- |
| VPS Server | 2 vCPU, 4GB RAM, 80GB SSD | ~$12–20/month |
| Domain | dxmpulse.com (or similar) | ~$10/year |
| TLS Certificate | Let’s Encrypt (via Caddy) | Free |
| SMTP Service | Resend / Mailgun / Amazon SES | $0–10/month (free tier) |
| Sentry | Free tier (5K errors/month) | Free |
| Backup Storage | S3-compatible (daily SQLite backup) | ~$1–5/month |

Estimated Monthly Cost: $25–40/month (infrastructure only)

# 6. Risk Management

## 6.1 Risk Register

| ID | Risk | Likelihood | Impact | Severity | Mitigation |
| --- | --- | --- | --- | --- | --- |
| R1 | SQLite write throughput exceeded under high traffic | Low | High | Medium | WAL mode handles 500+ writes/sec. Monitor query times. PostgreSQL migration path defined (Sprint 18+). |
| R2 | rrweb replay library instability (alpha version) | Medium | Medium | Medium | Chunked recording isolates failures. Replay is view-only (no data loss). Can pin version. |
| R3 | Chapa payment webhook failures or delays | Medium | High | High | Idempotent webhook handling. Manual activation via Telegram polling. Admin override endpoint. |
| R4 | Large event tables slow down dashboard queries | Medium | Medium | Medium | Indexed queries on (workspace_id, site_id, created_at). Event pruning strategy planned. |
| R5 | Session quota gaming (users creating multiple workspaces) | Low | Low | Low | Email uniqueness constraint. Manual review of suspicious signups. |
| R6 | SMTP delivery failures (emails not received) | Medium | Medium | Medium | Console fallback in dev. Structured logging of send attempts. Multiple SMTP provider options. |
| R7 | SDK script blocked by ad blockers or CSP on client sites | Medium | Medium | Medium | SDK served from custom domain (not analytics.* or tracker.*). Self-hosted, no third-party scripts. |
| R8 | Single-server failure (no redundancy) | Low | Critical | High | Daily SQLite backups. systemd auto-restart. Caddy health checks. Uptime monitoring alerts. |
| R9 | JWT token theft via XSS | Low | Critical | Medium | httpOnly cookies (not localStorage). CSP prevents inline scripts. No unsafe-eval. |
| R10 | Node.js / better-sqlite3 version mismatch blocking tests | Known | Medium | Medium | Rebuild native module with matching Node version. Fix planned in Sprint 15. |

## 6.2 Risk Response Strategy

| Strategy | Risks | Approach |
| --- | --- | --- |
| Mitigate | R1, R3, R4, R6, R8 | Implement preventive measures now (indexes, idempotency, backups, fallbacks) |
| Accept | R2, R5, R7 | Risk is low-impact or low-likelihood. Monitor and respond if triggered. |
| Avoid | R9 | Architecture decisions (httpOnly cookies, CSP) prevent the attack vector entirely |
| Fix | R10 | Known issue, scheduled fix in Sprint 15 (Node.js version alignment) |

# 7. Quality Management

## 7.1 Quality Assurance Activities

| # | Activity | When | Method |
| --- | --- | --- | --- |
| 1 | Build Verification | Every sprint completion | tsc (API) + vite build (Web), zero errors required |
| 2 | Input Validation | Every API endpoint | Zod schemas with min/max/format constraints |
| 3 | Security Review | Sprint 12 | CSP headers, rate limiting, HMAC verification, auth middleware |
| 4 | Error Handling | Sprint 12 | ErrorBoundary (frontend), global error handler (backend), Sentry (Sprint 13) |
| 5 | Manual Regression | Every sprint | Verify existing features still work after changes |
| 6 | Automated Testing | Sprint 15 (planned) | Integration tests for auth, billing, collect, alerts |
| 7 | Performance Testing | Sprint 14 (planned) | Bundle size audit, lazy loading verification, lighthouse audit |
| 8 | User Acceptance | Post-Sprint 14 | 5 agency users validate core workflows |

## 7.2 Code Quality Standards

- TypeScript strict mode throughout (apps/api + apps/web)

- Zod validation on every user-facing endpoint (no unvalidated input reaches business logic)

- Consistent error handling: try/catch in routes, global error handler, never leak stack traces

- Structured logging: JSON format with level, message, timestamp, requestId

- No console.log in production paths (replaced by structured logger)

- Minimal dependency policy: every new dependency requires explicit justification

## 7.3 Known Technical Debt

| # | Debt Item | Impact | Resolution Plan |
| --- | --- | --- | --- |
| TD1 | No automated tests (98 tests broken due to Node.js mismatch) | Cannot verify regressions automatically | Sprint 15: fix Node.js, write integration tests |
| TD2 | 547KB main bundle (no code splitting) | Slow initial load on poor networks | Sprint 14: lazy-load all pages |
| TD3 | No event data retention/pruning | Database grows unbounded | Sprint 18+: implement TTL-based event cleanup |
| TD4 | No database migration tool (raw ALTER TABLE) | Risk of migration failure on schema changes | Sprint 18+: consider migration library |
| TD5 | Console-based logging in some services | Inconsistent log format in production | Sprint 13: replace remaining console.log with logger |
| TD6 | No retry queue for failed notifications | Missed Telegram/email alerts on transient failures | Sprint 18+: simple retry with exponential backoff |

# 8. Communication Plan

## 8.1 Communication Channels

| Channel | Purpose | Frequency | Participants |
| --- | --- | --- | --- |
| Sprint Planning | Define scope, review plan, approve | Every sprint start | Product Lead + Dev |
| Sprint Review | Verify deliverables, identify gaps | Every sprint end | Product Lead + Dev |
| Build Verification | Confirm clean builds, no regressions | Every sprint end | Dev (automated) |
| Risk Review | Update risk register, review mitigations | Weekly | Product Lead |
| Beta Feedback | Collect user experience feedback | Ongoing (post-M6) | Product Lead + Beta Users |
| Documentation | SDLC document delivery and review | Per document completion | Product Lead + Dev |

## 8.2 Documentation Deliverables

| # | Document | Status | Reference |
| --- | --- | --- | --- |
| 1 | Product Overview (Vision) | Complete | DXM-VIS-2026-001 |
| 2 | Software Requirements Specification (SRS) | Complete | DXM-SRS-2026-001 |
| 3 | User Stories | Complete | DXM-US-2026-001 |
| 4 | High-Level Design (HLD) | Complete | DXM-HLD-2026-001 |
| 5 | Low-Level Design (LLD) | Complete | DXM-LLD-2026-001 |
| 6 | System Diagrams (UC, Sequence, ERD) | Complete | DXM-DIA-2026-001 |
| 7 | Project Management Plan (PMP) | Complete | DXM-PMP-2026-001 (this document) |
| 8 | Progress Notes | Planned | DXM-PRG-2026-001 |
| 9 | Software Test Document (STD) | Planned | DXM-STD-2026-001 |
| 10 | User Acceptance Testing (UAT) | Planned | DXM-UAT-2026-001 |

# 9. Deployment Plan

## 9.1 Deployment Strategy

Approach: Single-server deployment with reverse proxy

Target: Linux VPS (Ubuntu 22.04+)

Process: Manual deployment via SSH + systemd reload (CI/CD in Sprint 15)

## 9.2 Deployment Checklist

| # | Task | Responsible | Status |
| --- | --- | --- | --- |
| 1 | Provision VPS (2 vCPU, 4GB RAM) | Operations | Planned |
| 2 | Install Node.js 20 LTS + npm | Operations | Planned |
| 3 | Configure /etc/dxm-pulse.env with all required variables | Operations | Planned |
| 4 | Clone repo, npm install, npm run build (both apps) | Operations | Planned |
| 5 | Install systemd services (dxm-api, dxm-digest timer) | Operations | Planned |
| 6 | Configure Caddy with TLS (api.* + app.* + cdn.* routes) | Operations | Planned |
| 7 | Verify /health endpoint returns { status: ok, db: ok } | Operations | Planned |
| 8 | Configure SMTP credentials in env | Operations | Planned |
| 9 | Configure Sentry DSN in env (both SENTRY_DSN and VITE_SENTRY_DSN) | Operations | Planned |
| 10 | Set up external uptime monitor (UptimeRobot/Betterstack) | Operations | Planned |
| 11 | Configure daily SQLite backup (WAL checkpoint + copy) | Operations | Planned |
| 12 | Test signup → login → create site → install SDK → verify session received | Product Lead | Planned |
| 13 | Test Chapa payment flow (sandbox then production) | Product Lead | Planned |
| 14 | DNS configuration (A records for api/app/cdn subdomains) | Operations | Planned |

## 9.3 Rollback Strategy

- Git-based: every deployment is a tagged commit. Rollback = git checkout + systemd restart.

- Database: SQLite backup restored from daily backup. WAL checkpoint ensures consistency.

- Zero-downtime not required for MVP: systemd restart takes <5 seconds.

# 10. Budget Summary

## 10.1 Development Costs

| Item | Cost | Notes |
| --- | --- | --- |
| Development (AI-assisted) | Claude API usage | Per-sprint consumption, no fixed salary |
| Domain registration | ~$10/year | One-time annual cost |
| Development tools | $0 | All open-source: Node.js, React, SQLite, Caddy |

## 10.2 Monthly Operating Costs

| Item | Monthly Cost | Notes |
| --- | --- | --- |
| VPS hosting | $12–20 | Single server, scales vertically |
| SMTP service | $0–10 | Free tier covers early usage |
| Sentry monitoring | $0 | Free tier: 5K errors/month |
| Backup storage | $1–5 | S3-compatible daily backup |
| Total | $15–40/month | Covered by 1–2 Starter subscriptions |

## 10.3 Revenue Projections

| Metric | Month 1 | Month 3 | Month 6 | Month 12 |
| --- | --- | --- | --- | --- |
| Free users | 10 | 30 | 80 | 200 |
| Starter (499 ETB) | 2 | 8 | 20 | 50 |
| Pro (1,499 ETB) | 0 | 2 | 5 | 15 |
| Monthly Revenue (ETB) | 998 | 6,990 | 17,475 | 47,435 |
| Monthly Cost (ETB) | ~2,000 | ~2,000 | ~3,000 | ~5,000 |
| Net (ETB) | -1,002 | +4,990 | +14,475 | +42,435 |

# 11. Lessons Learned (Sprints 1–12)

| # | Lesson | Application |
| --- | --- | --- |
| L1 | Observability before testing: you can’t write meaningful tests without knowing what breaks in production | Moved monitoring (Sprint 13) before testing (Sprint 15) in the roadmap |
| L2 | Deploy early, iterate with real feedback: product decisions > engineering decisions | Beta launch planned after Sprint 14, not after all sprints complete |
| L3 | Minimal dependencies pay off: every library is a maintenance burden | Structured logger built in ~20 lines instead of adding winston/pino |
| L4 | AI-generated documentation works best when generated from actual code, not assumptions | All SDLC documents generated by reading real codebase, not from templates |
| L5 | Sprint ordering matters more than sprint speed | Reordered roadmap: observability → performance → testing (not testing first) |
| L6 | Feature gating should be designed from day one, not retrofitted | Plan-based feature gates built into both API (planSupportsFeature) and frontend (UpgradeGate) early |
| L7 | SQLite is surprisingly capable for MVP-scale SaaS when configured properly | WAL mode + proper indexes handles the target scale. PostgreSQL upgrade path preserved but not rushed. |
| L8 | Half-sprint iterations (.5, .6) are valuable for polish without scope creep | Used 10.5, 11.5, 11.6 to refine billing and reports without full sprint overhead |

End of Document

This PMP is a living document updated at each sprint boundary. All schedule dates are estimates subject to change based on sprint velocity and user feedback.